## Slide 1: NSOAP Drafting and Costing: Zambia
Dr. Mzaza Nthele
Director Clinical Care and Diagnostic Services
Ministry of Health
Rep. of Zambia
Notes: Zambia
First championed the effort at the WHA to prioritize emergency and essential services,
Then translated into efforts to strengthen the surgical system from paper to policy by embarking on a process to create a NSOASP

## Slide 2
Outline
  Draft compilation
  Costing strategy
  Lessons learned
Notes: Outline of the presentation.
Discuss how the draft was created, how the plan was costed and throughout discuss lesson learned along the way, advise to others.

## Slide 3
NSOAP Draft
  Compilation and prioritization of the committee discussions
  Reflection of the evidence-based approach
  Aligns with the priorities of the MOH
    Not a duplication of other MOH efforts
    Fits within the objectives of the overall national health strategic plan
Key Principles
Notes: First, key principles of creating an NSOAP draft.
Must be a reflection of the committee meeting and stakeholders discussions
Must align with the baseline assessemtents and situational anlaysis that was discussed
Given the need for

## Slide 4
NSOAP Draft
NSOAP Layout
Situational Analysis and Baseline Assessment
Main objectives, activities, and M&E plan for each domain
Costing plan

## Slide 5
Overview of Developmental Process
February – April 2016
May 2016
September 2016
Notes: Just a reminder of our process, the majority of the draft writing occurred during writing workshop which was a week long event with all major stakeholders.

## Slide 6
Drafting Process
Technical Working Group
Workforce
Service Delivery and Infrastructure
Financing, Information Management and Technology
Technical Review Panel
Writing Workshop
Notes:   But the material for the workshop came from the entire process,
  Starting with our original technical work group that was split up into three committees, the multiple meetings that led to a compilation of reports that was sent to the
  Technical review panel, that made sure each committee output aligned with the priorities of the MOH, and then that was re-evaluated again at the writing workshop with each domain being critically discussed
  That led to the final compilation of the draft.

## Slide 7
Committee Meetings
Main objective: create a report to be reviewed by the Technical Review Panel
  Report to Include:
    Outline of baseline assessments
    Actionable recommendations stratified in a tiered fashion to ensure implementation of the highest priority interventions
    Key metrics to monitor success
      Indicators and methods of monitoring success at 1,3 and 5 year timeframes
Example: Workforce
Notes: To discuss the drafting process, will quickly go through how this was done for service delivery as an example

## Slide 8
Utilized a Discussion Framework (previously called Terms of Reference) as a guide
Example: Workforce
Baseline Assessments
Key Indicators
Recommendations and M&E Plan
Notes: Utilized a discussion framework to guide these discussions and stay on task.
Example of work force discussion framework.
Identify the key indicators relevant to this topic
Baseline assessment / current situation
Decide upon recommendations and M& E plan

## Slide 9
Report from Committee Meetings
  Baseline Assessment and SWOT Analysis
Example: Workforce

## Slide 10
  Recommendations and M&E Plan
Example: Workforce
Notes: Example of some of the recommendations and M & E Plan

## Slide 11
Drafting Process
Technical Working Group
Workforce
Service Delivery and Infrastructure
Financing, Information Management and Technology
Technical Review Panel
Writing Workshop
Notes:   Next step, was the TRP

## Slide 12
Reviewed each report
Edited based on priorities of MOH and current initiatives
Technical Review Panel
Notes: Feel free to give examples

## Slide 13
Writing Workshop
Workforce
Service Delivery
Financing
Infrastructure
Information Management and Technology
Stakeholders
Main Aim: Compose, clarify and address key initiatives in terms of feasibility, impact and priority
  7 day event
  All major stakeholders and new members of MOH to facilitate appropriate language and structure
  Split up stakeholders again by domain
    Reviewed all initiatives, reported to large group
  Final SWOT analysis for accepted initiatives and objectives
  Development of Monitoring and Evaluation plan
Notes: Workshop participants split up again into the 5 domains of a NSOAP, went over the material again from the committee meetings
Plans were synthesized by each of the sub-committees and reported out to the entire group for further discussion and refinement.
Milestones and metrics were developed to be included within the upcoming National Health Strategic Plan, a five-year plan for 2017-2021.

## Slide 14
Writing Workshop
NSOAP Draft Organization
  Introduction
  Vision and overall goals of plan
  Chapter on each domain (infrastructure, service delivery, workforce, finance, information management, governance)
  Tables
    M&E plan with indicators
    Costing
Notes: Workshop participants split up again into the 5 domains of a NSOAP, went over the materila again from the committee meetings
Plans were synthesized by each of the sub-committees and reported out to the entire group for further discussion and refinement.
Milestones and metrics were developed to be included within the upcoming National Health Strategic Plan, a five-year plan for 2017-2021.

## Slide 15
Workforce Example
Workforce Chapter
Notes: Final product, Each domain with background info, an objective, strategy.
Using workforce as the example, Here are a few of the strategies or activities that we came up with.
Expand the establishment to provide positions……
Ensure equitable distribution of available SOA providers
Improve conditions of services, bonding, and retention mechanisms
Undertake regular curriculum reviews and maintain standards of education

## Slide 16
Workforce Example
Final Indicators, M&E
Notes: Here is how we organized what ind

## Slide 17
Lessons Learned:
Determining activities must be in the context of known baseline
Measures for implementation (indicators, monitoring and evaluation plan) must be discussed and agreed upon
Involvement of policy writers fluent in the language of MOH documents to ensure ease of incorporation into national health plan
Important for implementers to be part of the process to provide expertise in feasibility and execution of activities
Writing

## Slide 18
Main Aim: “Explore the art, science, and magic of connecting financial resources to the proposed activities.”
Similar structure to writing workshop (organized by domain)
Included Ministry of Finance specifically and other stakeholders
Each activity of the plan was costed
Based on initial costing, attendants prioritized strategies given the financial, workforce, and resource constraints
Costing Workshop
Notes: Costing should be performed for the whole Plan.
Strategic and thoughtful costed plan will also aide in discussions with funding bodies, implementation partners, and create more aid advocacy and appropriate utilization.

## Slide 19
How to Cost:
  Assemble available costing information
  Define the cost objects and the quantities
  Determine the cost base
  Validate Results
Key stakeholders:
  Government officials including NSOAP sponsors
  Policy experts, budget experts, technicians and costing experts
  Clinicians, health system administrators, professional organization representatives
  NGO/CSO actors, private sector representatives, and outside consultants
Costing

## Slide 20
Costing Example: Service Delivery
Notes: Now will use a strategy from our service delivery domain to discuss how we costed our plan.
One of our activites is to
“establish and strengthen the provision of quality essential and emergency surgical services
Plan to do through:
- implementing lifebox, WHO checklist, SafeObs, and SafePeds training programs
“ strengthen the capacity to care for trauma and injuries
- provide a trauma course at all level 1 hospitals
- provide surgical airways, tube thoracostomy, trauma laparotomy, management of non-displaced fractured, fracture reduction, irrigation and debridement of open fractures, external fixator placement

## Slide 21
Costing: By Inputs

## Slide 22
Costing: By Inputs

## Slide 23
Costing: Final Form

## Slide 24
Costing Summary
332,977,327.60 USD

## Slide 25
Costing: Most Critical Areas

## Slide 26
Lessons Learned:
Costing process highlights the value of different components of the plan
Evaluation of cost and impact ensures the best use of resources
Consultative process addresses concerns of feasibility, impact and priority
Costing

## Slide 27
Local Level:
Promote transparency
  Increase buy-in from clinical providers who are implementing the plan
Provides an opportunity for continued engagement and advocacy
  Opportunity to engage funders, media and ministry
International Level:
Sharing of ideas and innovations for improvement
  Problems similar, discussion of successful implementation strategies
Accountability
  Indicator collection and progress
Consensus building
  Standards, guidelines
Dissemination
Notes: We chose to have a National Surgical Forum with a panel in order to create full transparency and further engagement by clinical providers and hospital staff

## Slide 28
National Surgical, Obstetric, and Anesthesia Forum
Disseminated findings and goals of the plan
Over 50 members of government, advocacy, and professional societies, as well as members of the committees engaged in discussion
Panel members included professional society leaders, MOH, civil society and PGSSC
Increased buy-in from clinical providers
Opportunity to engage funders, media and ministry
Dissemination

## Slide 29
Questions?